## INFORMATION
BUG REPORT
PROJECT NAME | ReqRes API TEST
DESCRIPTION | COMPLE BUG REPORT OF ALL API WITH PROOF
TEST OBJECTIVE | TEST ALL API LISTED IN DOCUMENT
TEST CASE AUTHOR | SIVA KRISHNA
TEST CASE REVIEWER | *
TEST CASE VERSION | 1.O
TEST CASE EXECUTION DATE | 2025-03-22
TEST CASE CREATION DATE | 18/3/2025 TO 22/03/2025
TOOL USED | POSTMAN, EXCEL

## BUG REPORT
BUG_ID | TC_ID | TEST CASE | REQUEST TYPE | DESCRIPTION | STEPS | EXPECTED RESULT | ACTUAL RESULT | BUG STATUS | PRIORITY | INPUT DATA | ATTACHMENTS | COMMENTS | TESTED BY | TESTED DATE
BUG_01 | TC_04 | VERIFY THAT UNAVAILABLE PARAMETER SHOW ERROR | GET | users HAVE 2 PAGES IF I ENTER page=99 THAN IT IS NOT SHOWING ERROR | 1. GO TO API https://reqres.in/api/users?page=99 2. CREATE GET REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 404 NOT FOUND 2. NO DATA SHOWN | 1. 200 OK 2. DONE | IN PROGRESS | MINOR | PAGE=99 | https://drive.google.com/file/d/1BkIZCfDFE5aDO8KTQIVfrnOe93cQKof_/view?usp=sharing | DATABASE HAVE ONLY 2 PAGES
BUG_02 | TC_06 | VERIFY THAT UNAVAILABLE PARAMETER SHOW ERROR | GET | users HAVE 2 PAGES IF I ENTER page=ABC THAN IT IS SHOWING DATA | 1. GO TO API https://reqres.in/api/users?page=ABC 2. CREATE GET REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 404 NOT FOUND 2. NO DATA SHOWN | 1. 200 OK 2. DATA SHOWN | IN PROGRESS | BLOCKER | PAGE=ABC | https://drive.google.com/file/d/1GaSTP_WXcUIuV_zY7G3Aup0XZpVGBJb0/view?usp=drive_link | DATABASE HAVE NO PAGE WITH A
BUG_03 | TC_10 | VERIFY THAT USER CREATED AND 201 RESPONSE CODE | POST | WHEN NEW USER CREATED BUT NEW USER NOT SHOWING WHEN CREATE GET REQUEST | 1. GO TO API https://reqres.in/api/users 2. CREATE POST REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 201 CREATED 2. THE NEW USER DATA CREATED AND SHOWN TO DATABASE | 1. DONE 2. CREATE DATA NOT SHOWN WHEN I CREATE GET REQUEST ON THIS API | IN PROGRESS | MAJOR | { "id": 7, "email": "michael.lawson@reqres.in", "first_name": "Michael", "last_name": "Lawson", "avatar": "https://reqres.in/img/faces/7-image.jpg" } | https://drive.google.com/file/d/1ZhWuaZO5In2ZzBCgYZu0FwPxu-qrNIR_/view?usp=drive_link | SCREENSHOT ATTACHED IN BUG REPORT THERE WE CAN SEE THAT USER GENERATED WITH 1D=13 BUT DATABASE HAVE NO THIS TYPE OF DATA WHEN LISTING ALL USERS(DATABASE NOT UPDATED)
BUG_04 | TC_11 | VERIFY THAT USER DATA UPDATED SUCCESSFULLY | PUT | THE RESPONSE SHOW THAT THE DATABASE UPDATED BUT ACTUALLY JUST SHOWING NOT UPDATED | 1. GO TO API https://reqres.in/api/users/2 2. CREATE PUT REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 200 OK 2. USER DATA UPDATED AND SHOWN IN DATABASE | 1. DONE 2. UPDATED USER DATA NOT SHOWING, OLD IS AS IT IS | IN PROGRESS | MAJOR | { "id": 7, "email": "michael123.lawson@reqres.in", "first_name": "Michael123", "last_name": "Lawson123", "avatar": "https://reqres.in/img/faces123/7-image.jpg" } | https://drive.google.com/file/d/1JE9GfAU6YB8c0_e6QX5pdYlQtrL4vAZw/view?usp=drive_link | HERE IN SCREENSHOT WE CAN SEE THAT DATA UPDATED BUT ACTUALLY NOT
BUG_05 | TC_12 | VERIFY THAT USER DATA UPDATED SUCCESSFULLY | PATCH | THE RESPONSE SHOW THAT THE DATABASE UPDATED BUT ACTUALLY JUST SHOWING NOT UPDATED | 1. GO TO API https://reqres.in/api/users/2 2. CREATE PATCH REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 200 OK 2. USER DATA UPDATED AND SHOWN IN DATABASE | 1. DONE 2. UPDATED USER DATA NOT SHOWING, OLD IS AS IT IS | IN PROGRESS | MAJOR | { "first_name": "123", } | https://drive.google.com/file/d/1uQFnLTLkO3y_TyCDaEG7aQ-lXPOn_ins/view?usp=drive_link | HERE IN SCREENSHOT WE CAN SEE THAT DATA UPDATED BUT ACTUALLY NOT
BUG_06 | TC_13 | VERIFY THAT USER DATA DELETED AND NOT SHOWN | DELETE | RESPONSE JUST SHOWING BUT ACCOUNT NOT DELETED | 1. GO TO API https://reqres.in/api/users/2 2. CREATE DELETE REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 204 NO CONTENT 2. USER DATA DELETED AND NOT SHOWN IN DATABASE | 1. DONE 2. USER DATA NOT DELETED AND WHEN USER REQUEST THAN SHOWN | IN PROGRESS | MAJOR | NA | https://drive.google.com/file/d/15qDqZEcTzyVzolgmzwT9kXPIYzdsKuG2/view?usp=drive_link https://drive.google.com/file/d/1_h-Gu-ew9XPnxMNIAv6n3j7xMLClxgeE/view?usp=drive_link | NA
BUG_07 | TC_18 | VERIFY THAT IF PAGE NUMBER NOT AVAILABLE THAN DATA NOT SHOWN AND ERROR GENERATED | GET | users HAVE 2 PAGES IF I ENTER page=99 THAN IT IS NOT SHOWING ERROR | 1. GO TO API https://reqres.in/api/unknown?page=99 2. CREATE GET REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 404 NOT FOUND 2. DATA NOT SHOWN | 1. 200 OK 2. SOME DATA SHOWN | IN PROGRESS | MAJOR | PAGE = 99 | https://drive.google.com/file/d/15hBZdv1yYWjHYliUyIpFat6CMnm2SQF8/view?usp=drive_link | IF PAGE 99 NOT AVAILABLE THAN GENERATE 404 AND DON’T SHOW ANYTYPE OF DATA BUT HERE SOME DATA SHOWN
BUG_08 | TC_19 | VERIFY THAT IF PAGE NUMBER PARAMETER DIFFERENT THAN ERROR GENERATED AND DATA NOOT SOWN | GET | users HAVE 2 PAGES IF I ENTER page=ABC THAN IT IS SHOWING DATA | 1. GO TO API https://reqres.in/api/unknown?page=AB 2. CREATE GET REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 404 NOT FOUND 2. DATA NOT SHOWN | 1. 200 OK 2. DATA SHOWN | IN PROGRESS | BLOCKER | PAGE = AB | https://drive.google.com/file/d/1IO6wrEp_mKM-l2D7_DO92AZPSAPbng-u/view?usp=drive_link | IF PAGE 99 NOT AVAILABLE THAN GENERATE 404 AND DON’T SHOW ANYTYPE OF DATA BUT HERE SOME DATA SHOWN
BUG_09 | TC_24 | VERIFY THAT RESOURCE CREATED AND SHOWN SUCCESSFULLY | POST | REPONSE SHOWN FOR RESOURCE CREATED BUT ACTUALLY NOT CREATED AND NOT SHOWING | 1. GO TO API https://reqres.in/api/unknown 2. CREATE GET REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 201 CREATED 2. THE NEW USER DATA CREATED AND SHOWN TO DATABASE | 1. DONE 2. USER CAN UNABLE TO RETRIEVE THAT DATA, JUST SHOWN BUT ACTULLY NOT CREATED | IN PROGRESS | MAJOR | NA | https://drive.google.com/file/d/1SV-2mQqgwJ38rr9lyB5gAzMpSqSJqbuS/view?usp=drive_link | RESOURCE CREATED BUT NOT UPDATED AND NOT SHOWN
BUG_10 | TC_25 | VERIFY THAT RESOURCE UPDATED SUCCESSFULLY | PUT | REPONSE SHOWN FOR RESOURCE CREATED BUT ACTUALLY NOT CREATED AND NOT SHOWING | 1. GO TO API https://reqres.in/api/unknown/2 2. CREATE PUT REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 200 OK 2. RESOURCE UPDATED AND SHOWN IN DATABASE | 1. DONE 2. UPDATED RESOURCE NOT SHOWING, OLD IS AS IT IS | IN PROGRESS | MAJOR | { "id": .111, "name": "123cerulean", "year": 2000123, "color": "#98B2D1123", "pantone_value": "15-123-4020" } | https://drive.google.com/file/d/1K_teL97VEmm0cDUEnH__isITji02lR9j/view?usp=drive_link | RESOURCE UPDATED BUT NOT SHOWING WHEN TRYING TO RETIRIEVE IT
BUG_11 | TC_26 | VERIFY THAT PARTIAL RESOURCE UPDATED SUCCESSFULLY | PATCH | RESOURCE NOT UPDATED RETURN AS IT IS | 1. GO TO API https://reqres.in/api/unknown/2 2. CREATE PATCH REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 200 OK 2. RESOURCE UPDATED AND SHOWN IN DATABASE | 1. DONE 2. UPDATED RESOURCE NOT SHOWING, OLD IS AS IT IS | IN PROGRESS | MAJOR | { "year": 23 } | https://drive.google.com/file/d/1XJKnt1sMKxek8eJegp26oDvh1fiMDOnV/view?usp=drive_link | RESOURCE UPDATED BUT NOT SHOWING WHEN TRYING TO RETIRIEVE IT
BUG_12 | TC_27 | VERIFY THAT RESOURCE DELETED AND NOT SHOWN | DELETE | RESOURCE NOT DELETED JUST RESPONSE SHOWN | 1. GO TO API https://reqres.in/api/unknown/2 2. CREATE DELETE REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 204 NO CONTENT 2. RESOURCE DELETED AND NOT SHOWN IN DATABASE | 1. DONE 2. RESOURCE NOT DELETED AND WHEN USER REQUEST THAN SHOWN | IN PROGRESS | MAJOR | NA | https://drive.google.com/file/d/15qDqZEcTzyVzolgmzwT9kXPIYzdsKuG2/view?usp=drive_link | IN SCREEN SHOWN THAT NO DATA BUT ACTUALLY DATA NOT DELETED
BUG_13 | TC_29 | VERIFY THAT USER CAN REGISTER SUCCESSFULLY | POST | AFTER REGISTER DATA NOT SHOWN AND GENERATED TOKEN & ID IS FAKE | 1. GO TO API https://reqres.in/api/register 2. CREATE POST REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 200 OK 2. GENERATED DATA RETRIEVED BY USER 3. TOKEN AND ID GENERATED | 1. DONE 2. USER UNABLE TO GET REGISTERED DATA AND ID GENERATED IS RANDOM AND FAKE 3. DONE | IN PROGRESS | MAJOR | { "email": "eve.holt@reqres.in", "password": "pistol" } | https://drive.google.com/file/d/1tSCGtcUyo1w4h94D3s3v0Z078r12ukA2/view?usp=drive_link | NA
BUG_14 | TC_30 | VERIFY THAT USER CAN REGISTER SUCCESSFULLY | POST | WRONG ERROR MESSAGE SHOWN | 1. GO TO API https://reqres.in/api/register 2. CREATE POST REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 400 BAD REQUEST 2. MESSAGE SHOWN THAT USERNAME REQUIRED ( "error": "Missing USERNAME ) | 1. DONE 2. "error": "Missing email or username" > USERNAME IS NOT REQUIRED IN THIS ERROR BECAUSE USERNAME IS AVAILBALE | IN PROGRESS | MINOR | { "password": "pistol" } | https://drive.google.com/file/d/1LWUf8-SRcmuxRCyBGxy3h40lpieRaF7i/view?usp=drive_link | NA
BUG_15 | TC_32 | VERIFY THAT USER CAN REGISTER SUCCESSFULLY | POST | WRONG ERROR MESSAGE SHOWN | 1. GO TO API https://reqres.in/api/register 2. CREATE POST REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 404 BAD REQUEST 2. "error": "Missing email AND username" | 1. DONE 2. "error": "Missing email or username" | IN PROGRESS | MINOR | NA | https://drive.google.com/file/d/11HFml3rxG7rzOWXHujfV4IesYfBiOI-a/view?usp=drive_link | NA
BUG_16 | TC_34 | VERIFY THAT USER CAN NOT LOGIN AND ERROR MESSAGE GENERATED | POST | HERE USER CAN LOGIN WITH THE WRONG USERNAME | 1. GO TO API https://reqres.in/api/login 2. CREATE POST REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 404 BAD REQUEST 2. ERROR : INCORRECT PASSWORD 3. LOGIN FAIL | 1. 200 OK 2. NO ERROR 3. LOGIN SUCCESS | IN PROGRESS | BLOCKER | { "email": "eve.holt@reqres.in", "password": "cityslicka123" } | https://drive.google.com/file/d/1kZ8lG4EwGvwzAiQAB5_yLfbAZpouLfZx/view?usp=drive_link | NA
BUG_17 | TC_39 | VERIFY THAT USER CAN NOT LOGIN AND ERROR MESSAGE GENERATED | POST | WRONG ERROR MESSAGE SHOWN | 1. GO TO API https://reqres.in/api/login 2. CREATE POST REQUEST 3. CREATE SOME RELATED TEST SCRIPTS 4. RUN AND NOTE THE RESPONSE | 1. 404 BAD REQUEST 2. ERROR : MISSING USERNAME AND PASSWORD 3. LOGIN FAIL | 1. DONE 2. MISSING USERNAME OR PASSWORD 3. DONE | IN PROGRESS | MINOR | NA | https://drive.google.com/file/d/1PFqrPBiznNn_2a3sO78N_X19JfjI8_Xm/view?usp=drive_link | NA